## MEN'S CALENDAR PROPOSAL (hidden)
Go back to Table of Contents
Pre-Dev
START WEEK 39 DUE TO CNY BLACKOUT
|  |  | PROPOSED |  |  |  | PROPOSED |  |  |  |  | PROPOSED
| Buying Period |  |  | SUMMER 2019 Collection (M1/M2) | SUMMER 2019 Chase (M3) |  |  | FALL 2019 Collection (M1/M2) | FALL 2019 Chase (M3) |  | FALL 2019 Sweaters (M2) |  | HOLIDAY 2019 Collection M1/M2 | HOLIDAY 2019 Chase (M3) |  |  | SPRING 2020 Collection M1/M2 |  |  | SUMMER 2020 |  |  | EARLY BTS 2020 |  |  | FALL 2020 |  |  | HOLIDAY 2020 |  |  | SPRING 2021
| IN DC |  |  | 4/1 ndc | 4/1 ndc |  |  | 7/1 NDC | 7/1 NDC |  |  |  | 10/1 NDC | 10/1 NDC |  |  | 1/1 NDC | 1/1 NDC |  | 4/1 NDC |  |  | 7/1 NDC |  |  | 8/1 NDC |  |  | 10/1 NDC |  |  | 1/1 NDC
Selling Period
| Week # | Week Start (Monday) | Weeks to IN DC | Meetings |  | Deadlines & Handoffs | Weeks to IN DC | Meetings |  | Deadlines & Handoffs |  | Weeks to IN DC | Meetings |  | Deadlines & Handoffs |  |  |  | Weeks to IN DC |  |  | Weeks to IN DC | [5 empty] | Weeks to IN DC |  |  | Weeks to IN DC
| 23 | 2017-07-03
| 24 | 2017-07-10
| 25 | 2017-07-17
| 26 | 2017-07-24
| 27 | 2017-07-31
| 28 | 2017-08-07
| 29 | 2017-08-14
| 30 | 2017-08-21
| 31 | 2017-08-28
| 32 | 2017-09-04
| 33 | 2017-09-11
| 34 | 2017-09-18
| 35 | 2017-09-25
| 36 | 2017-10-02
| 37 | 2017-10-09
| 38 | 2017-10-16
| 39 | 2017-10-23
| 40 | 2017-10-30
| 41 | 2017-11-06
| 42 | 2017-11-13
| 43 | 2017-11-20
| 44 | 2017-11-27
| 45 | 2017-12-04
| 46 | 2017-12-11
| 47 | 2017-12-18
| 48 | 2017-12-25
| 49 | 2018-01-01
| 50 | 2018-01-08
| 51 | 2018-01-15
| 52 | 2018-01-22
| 53 | 2018-01-29
| 1 | 2018-02-05
| 2 | 2018-02-12
| 3 | 2018-02-19
| 4 | 2018-02-26
| 5 | 2018-03-05
| 6 | 2018-03-12
| 7 | 2018-03-19
| 8 | 2018-03-26
| 9 | 2018-04-02
| 10 | 2018-04-09
| 11 | 2018-04-16
| 12 | 2018-04-23
| 13 | 2018-04-30
| 14 | 2018-05-07
| 15 | 2018-05-14
| 16 | 2018-05-21
| 17 | 2018-05-28
| 18 | 2018-06-04
| 19 | 2018-06-11
| 20 | 2018-06-18
| 21 | 2018-06-25
| 22 | 2018-07-02
| 23 | 2018-07-09
| 24 | 2018-07-16
| 25 | 2018-07-23
| 26 | 2018-07-30 | 36 |  |  |  | 48 | RAW MAT JACKET AND SWEATER YARN ALIGNMENT (T) |  | Need initial silhouette direction from concept for sweaters and jackets mocks Sweater and Jackets only
| 27 | 2018-08-06 | 35 |  |  |  | 47
| 28 | 2018-08-13 | 34 |  |  |  | 46 | FABRIC/TRIM/EMBELLISHMENT ALIGNMENT (T) JACKET AND YARN FABRIC SHOWBACK (T) |  | Need initial silhoutte direction from concept for mocks This is initial raw mat with pack complete and soft copy distro ; deadline only no presentation
| 29 | 2018-08-20 | 33 |  |  |  | 45
| 30 | 2018-08-27 | 32 | LAUNCH YARDAGE/ART X |  |  | 44
| 31 | 2018-09-03 | 31 |  |  |  | 43
| 32 | 2018-09-10 | 30 |  |  |  | 42
| 33 | 2018-09-17 | 29 |  |  |  | 41
| 34 | 2018-09-24 | 28 |  |  |  | 40
| 35 | 2018-10-01 | 27 | SEASONAL CONCEPT AND LINE PLAN |  |  | 39 | RAW MAT FABRIC PASS OFF TO SOURCING (T)
| 36 | 2018-10-08 | 26 | WORKING ALIGNMENT MEETNIGS |  |  | 38
| 37 | 2018-10-15 | 25 | SET UPS/ TPX (M/F) |  |  | 37 | FABRIC SHOWBACK (T) |  | Women's BTS Fabric showback 10/16
| 38 | 2018-10-22 | 24 | SET UPS/ TPX (M/F) |  |  | 36 | INITIAL SEASONAL CONCEPT - WALL BUILD OUT (M)
| 39 | 2018-10-29 | 23 |  |  |  | 35 | WALL COMPLETE - PATTERN, PRINT, COLOR (M) |  | Review initial fabric with Colby and buying leads
| 40 | 2018-11-05 | 22 |  |  | latest date for art x for strikeoffs at poho (F) | 34 | LAUNCH YARDAGE/ART X (F) |  | ORDER SAMPLE AND MOCKING YDGE
| 41 | 2018-11-12 | 21 | SAMPLES X (F) |  |  | 33 |  |  | MOCKING YARDAGE SENT
| 42 | 2018-11-19 | 20 | SAMPLE REVIEW (T) EARLY COMMIT/ FABRIC BOOKING MEETING (W) |  |  | 32 |  |  | MOCKING BEGINS
| 43 | 2018-11-26 | 19 |  |  |  | 31 |  |  | MOCKING
| 44 | 2018-12-03 | 18 | FPR (Th) POHO JACKETS (F) |  | Strikeoffs x (F) | 30 | SEASONAL CONCEPT (T) AND LINE PLAN (Th) PATTERN OVERVIEW (T?)
| 45 | 2018-12-10 | 17 | POHO (M) |  | move poho to 12/10 due to travel and later fpr; may need to early commit week prior | 29 | WORKING ALIGNMENT MEETINGS - Jackets (W) |  | Team working sessions with some initial sketches, tears and vintage garments, design mocks
| 46 | 2018-12-17 | 16 |  |  |  | 28 | SET UPS/TPX - Jacket (M/F) |  | Sweater and jacket set ups and tpx; China art x for strikeoffs ID Tailoring bodies
| 47 | 2018-12-24 | 15 |  |  |  | 27 |  |  |  |  | 40
| 48 | 2018-12-31 | 14 |  | Chase Meeting (T) |  | 26 |  |  |  |  | 39
| 49 | 2019-01-07 | 13 |  | Chase set ups/tpx (M/F) |  | 25 |  |  |  | SAMPLE YARN ORDER DUE | 38 | RAW MAT FABRIC PASS OFF TO SOURCING (T) |  | Earlier due to CNY
| 50 | 2019-01-14 | 12 |  |  |  | 24 | WORKING ALIGNMENT MEETINGS - Wovens, Knits, Bottoms(W) SAMPLE REVIEW JACKETS (T) |  | Sweater and Jacket samples x |  | 37
| 51 | 2019-01-21 | 11 |  |  |  | 23 | FPR JACKETS (T) POHO JACKETS (Th) PRIORITY SET UPS/ TPX - Wovens, Knits, Bottoms (M/F) W1 |  |  |  | 36 | FABRIC SHOWBACK (T)
| 52 | 2019-01-28 | 10 |  | CHASE SAMPLES X (F) |  | 22 | SET UPS/ TPX - Wovens, Knits, Bottoms (M/F) PRINT WRAPAROUND (Th) W2 |  |  |  | 35
| 1 | 2019-02-04 | 9 |  | chase poho (F) (13 wks to month 2 ndc; 17 wks to month 3) |  | 21 |  |  |  | SKETCH REVIEW | 34
| 2 | 2019-02-11 | 8 |  |  |  | 20 |  |  | latest date for art x for strikeoffs at poho (F) (Non-china) | TPX + LAB DIP REQUESTS | 33
| 3 | 2019-02-18 | 7 |  |  |  | 19 | SAMPLE REVIEW JACKETS (T) |  |  |  | 32 | INITIAL SEASONAL CONCEPT - WALL BUILD OUT (M)
| 4 | 2019-02-25 | 6 |  |  |  | 18 | FPR JACKETS (T) POHO JACKETS (Th) |  | Woven, knits, bottoms samples x |  | 31 | WALL COMPLETE - PATTERN, PRINT, COLOR (M) |  | Review initial fabric with Colby and buying leads
| 5 | 2019-03-04 | 5 | SHIP VSSL | SHIP VSSL |  | 17 | SAMPLE REVIEW PREP (T); SAMPLE REVIEW (Th) EARLY COMMIT/ FABRIC BOOKING MEETING (Th) |  |  |  | 30 | LAUNCH YARDAGE/ART X (F) |  | ORDER SAMPLE AND MOCKING YDGE
| 6 | 2019-03-11 | 4 |  |  |  | 16 | Buying to pass ITB information/same format as POHO doc |  | Strikeoffs x (F) | SAMPLE X DATE | 29 |  |  | MOCKING YARDAGE SENT
| 7 | 2019-03-18 | 3 |  |  |  | 15 | FPR (T) POHO (F) |  |  | SAMPLE REVIEW (T) | 28 |  |  | MOCKING BEGINS
| 8 | 2019-03-25 | 2 |  |  |  | 14 |  | Chase Meeting (T) |  | FPR (T) POHO (F) | 27 |  |  | MOCKING
| 9 | 2019-04-01 | 1 | SHIP AIR | SHIP AIR |  | 13 |  | Chase set ups/tpx (M/F) |  |  | 26 | SEASONAL CONCEPT (T) AND LINE PLAN (Th) PATTERN OVERVIEW (T) |  |  | 39
| 10 | 2019-04-08 | 0 | NDC | NDC |  | 12 |  |  |  |  | 25 | WORKING ALIGNMENT MEETINGS - Jackets (W) |  | Team working sessions with some initial sketches, tears and vintage garments, design mocks | 38
| 11 | 2019-04-15 |  |  |  |  | 11 |  |  |  |  | 24 | WORKING ALIGNMENT MEETINGS - Wovens, Knits, Bottoms (W) SET UPS/TPX - Jacket (M/F) |  |  | 37
| 12 | 2019-04-22 |  |  |  |  | 10 |  | CHASE SAMPLES X (F) |  |  | 23 | SET UPS/ TPX - Wovens, Knits, Bottoms (M/F) W1 |  |  | 36 | RAW MAT FABRIC PASS OFF TO SOURCING (T)
| 13 | 2019-04-29 |  |  |  |  | 9 |  | chase poho (F) (13 wks to month 2 ndc; 17 wks to month 3) |  |  | 22 | SET UPS/ TPX - Wovens, Knits, Bottoms (M/F) W2 PRINT WRAPAROUND (Th) |  |  | 35
| 14 | 2019-05-06 |  |  |  |  | 8 |  |  |  |  | 21 |  |  |  | 34 | FABRIC SHOWBACK (T)
| 15 | 2019-05-13 |  |  |  |  | 7 |  |  |  |  | 20 |  |  | latest date for art x for strikeoffs at poho (F) Sweater and Jacket samples x | 33 | INITIAL SEASONAL CONCEPT - WALL BUILD OUT (M)
| 16 | 2019-05-20 |  |  |  |  | 6 |  |  |  |  | 19 | SAMPLE REVIEW JACKETS (T) |  |  | 32 | WALL COMPLETE - PATTERN, PRINT, COLOR (M) | Review initial fabric with Colby and buying leads
| 17 | 2019-05-27 |  |  |  |  | 5 |  |  |  |  | 18 | FPR JACKETS (T) POHO JACKETS (Th) |  | Woven, knits, bottoms samples x | 31 | LAUNCH YARDAGE/ART X (F) | ORDER SAMPLE AND MOCKING YDGE
| 18 | 2019-06-03 |  |  |  |  | 4 | SHIP VSSL | SHIP VSSL |  |  | 17 | SAMPLE REVIEW PREP (T); SAMPLE REVIEW (Th) EARLY COMMIT/ FABRIC BOOKING MEETING (Th) |  |  | 30 |  | MOCKING YARDAGE SENT
| 19 | 2019-06-10 |  |  |  |  | 3 |  |  |  |  | 16 | FPR (TH) |  | Strikeoffs x (F) | 29 |  | MOCKING BEGINS
| 20 | 2019-06-17 |  |  |  |  | 2 | SHIP AIR | SHIP AIR |  |  | 15 | POHO (F) |  |  | 28 |  | MOCKING
| 21 | 2019-06-24 |  |  |  |  | 1 |  |  |  |  | 14 |  | Chase Meeting (T) |  | 27 | SEASONAL CONCEPT (T) AND LINE PLAN (Th) PATTERN OVERVIEW (T) SAMPLE YARN ORDER DUE FOR SWEATERS
| 22 | 2019-07-01 |  |  |  |  | 0 | NDC | NDC |  | SHP VSL | 13 |  | Chase set ups/tpx (M/F) |  | 26 |  | July 4th holiday
| 23 | 2019-07-08 | [9 empty] | 12 |  |  |  | 25 | WORKING ALIGNMENT MEETINGS - Sweaters and Jackets (W) | Team working sessions with some initial sketches, tears and vintage garments, design mocks
| 24 | 2019-07-15 | [9 empty] | 11 |  |  |  | 24 | WORKING ALIGNMENT MEETINGS - Wovens, Knits, Bottoms(W) + Priority SET UPS/TPX - Sweaters and Jacket |  | 37 | RAW MAT FABRIC PASS OFF TO SOURCING (T)
| 25 | 2019-07-22 | [8 empty] | SHP AIR | 10 |  | CHASE SAMPLES X (F) |  | 23 | SET UPS/TPX - Sweaters and Jacket (M/F) |  | 36
| 26 | 2019-07-29 | [9 empty] | 9 |  | chase poho (F) (13 wks to month 2 ndc; 17 wks to month 3) |  | 22 | SET UPS/ TPX - Wovens, Knits, Bottoms (M/F) PRINT WRAPAROUND (Th) |  | 35 | FABRIC SHOWBACK (T)
| 27 | 2019-08-05 | [8 empty] | NDC | 8 |  |  |  | 21 |  |  | 34 | INITIAL SEASONAL CONCEPT - WALL BUILD OUT (M)
| 28 | 2019-08-12 | [9 empty] | 7 |  |  |  | 20 |  | latest date for art x for strikeoffs at poho (F) | 33 | WALL COMPLETE - PATTERN, PRINT, COLOR (M) | Review initial fabric with Colby and buying leads
| 29 | 2019-08-19 | [9 empty] | 6 |  |  |  | 19 |  | Sweater and Jacket samples x | 32 | LAUNCH YARDAGE/ART X (F) | ORDER SAMPLE AND MOCKING YDGE
| 30 | 2019-08-26 | [9 empty] | 5 |  |  |  | 18 | SAMPLE REVIEW SWEATERS AND JACKETS (T) | Woven, knits, bottoms samples x | 31 |  | MOCKING YARDAGE SENT
| 31 | 2019-09-02 | [9 empty] | 4 | SHIP VSSL | SHIP VSSL |  | 17 | FPR FOR SWEATERS AND JACKETS (T) POHO (Th) SAMPLE REVIEW PREP (W); SAMPLE REVIEW (Th) EARLY COMMIT/ FABRIC BOOKING MEETING (Th) |  | 30 |  | MOCKING BEGINS
| 32 | 2019-09-09 | [9 empty] | 3 |  |  |  | 16 |  | Strikeoffs x (F) | 29 |  | MOCKING
| 33 | 2019-09-16 | [9 empty] | 2 | SHIP AIR | SHIP AIR |  | 15 | FPR (T) POHO (F) |  | 28 | SEASONAL CONCEPT (T) AND LINE PLAN (Th) PATTERN OVERVIEW (T) |  | 42 | RAW MAT FABRIC PASS OFF TO SOURCING (T)
| 34 | 2019-09-23 | [9 empty] | 1 |  |  |  | 14 | Chase Meeting (T) |  | 27 | WORKING ALIGNMENT MEETINGS - Sweaters and Jackets (W) |  | 41
| 35 | 2019-09-30 | [9 empty] | 0 | NDC | NDC |  | 13 | Chase set ups/tpx (M/F) |  | 26 | WORKING ALIGNMENT MEETINGS - Wovens, Knits, Bottoms(W) |  | 40 | FABRIC SHOWBACK (T)
| 36 | 2019-10-07 | [13 empty] | 12 |  |  | 25 | SET UPS/TPX - Sweaters and Jacket (M/F) |  | 39 | INITIAL SEASONAL CONCEPT - WALL BUILD OUT (M)
| 37 | 2019-10-14 | [13 empty] | 11 |  |  | 24 |  |  | 38 | WALL COMPLETE - PATTERN, PRINT, COLOR (M) | Review initial fabric with Colby and buying leads |  | RAW MAT FABRIC PASS OFF TO SOURCING (T)
diwali | 38 | 2019-10-21 | [13 empty] | 10 | CHASE SAMPLES X (F) |  | 23 |  |  | 37 | LAUNCH YARDAGE/ART X (F) | ORDER SAMPLE AND MOCKING YDGE
diwali | 39 | 2019-10-28 | [13 empty] | 9 | chase poho (F) (13 wks to month 2 ndc; 17 wks to month 3) |  | 22 | SET UPS/ TPX - Wovens, Knits, Bottoms (M/F) PRINT WRAPAROUND (Th) |  | 36 |  | MOCKING YARDAGE SENT |  | FABRIC SHOWBACK (T)
| 40 | 2019-11-04 | [13 empty] | 8 |  |  | 21 |  | Sweater and Jacket samples x | 35 |  | MOCKING BEGINS |  | INITIAL SEASONAL CONCEPT - WALL BUILD OUT (M)
| 41 | 2019-11-11 | [13 empty] | 7 |  |  | 20 | SAMPLE REVIEW SWEATERS AND JACKETS (T) | latest date for art x for strikeoffs at poho (F) | 34 |  | MOCKING |  | WALL COMPLETE - PATTERN, PRINT, COLOR (M) | Review initial fabric with Colby and buying leads
| 42 | 2019-11-18 | [13 empty] | 6 |  |  | 19 | FPR SWEATERS AND JACKETS (T) POHO SWEATERS AND JACKETS (Th) |  | 33 |  |  | 37 | LAUNCH YARDAGE/ART X (F) | ORDER SAMPLE AND MOCKING YDGE
| 43 | 2019-11-25 | [13 empty] | 5 |  |  | 18 |  | Woven, knits, bottoms samples x | 32 |  |  | 36 |  | MOCKING YARDAGE SENT
| 44 | 2019-12-02 | [10 empty] | Chase month 3 NDC |  |  | 4 | SHIP VSSL | SHIP VSSL | 17 | SAMPLE REVIEW PREP (T) EARLY COMMIT/ FABRIC BOOKING MEETING (Th) |  | 31 | WORKING ALIGNMENT MEETINGS - Sweaters and Jackets (W) - China Only |  | 35 |  | MOCKING BEGINS
| 45 | 2019-12-09 | [13 empty] | 3 |  |  | 16 | SAMPLE REVIEW (T) | Align on chase ideas for Month 2/3 Strikeoffs x | 30 | WORKING ALIGNMENT MEETINGS - Wovens, Knits, Bottoms(W) - China Only SET UPS/TPX - Sweaters and Jacket (M/F) PRINT WRAPAROUND (Th) |  | 34 |  | MOCKING
| 46 | 2019-12-16 | [13 empty] | 2 | SHIP AIR | SHIP AIR | 15 | FPR (Th) POHO (F) |  | 29 | SET UPS/ TPX - Wovens, Knits, Bottoms (M/F) |  | 33 | SEASONAL CONCEPT (T) AND LINE PLAN (Th) PATTERN OVERVIEW (T) |  |  | RAW MAT FABRIC PASS OFF TO SOURCING (T) | china mills
| 47 | 2019-12-23 | [13 empty] | 1 |  |  | 14 |  |  | 28 |  |  | 32
| 48 | 2019-12-30 | [13 empty] | 0 | NDC | NDC | 13 |  |  | 27 |  |  | 31
| 49 | 2020-01-06 | [16 empty] | 12 | Chase Meeting (T) | chase non china due to cny | 26 |  |  | 30
| 50 | 2020-01-13 | [16 empty] | 11 | Chase set ups/tpx - Non China |  | 25 | WORKING ALIGNMENT MEETINGS - Sweaters and Jackets (W) - Non-China |  | 29
| 51 | 2020-01-20 | [16 empty] | 10 |  |  | 24 | WORKING ALIGNMENT MEETINGS - Wovens, Knits, Bottoms(W) - Non-China SET UPS/TPX - Sweaters and Jacket (M/F) PRINT WRAPAROUND (Th) |  | 28
| 52 | 2020-01-27 | [16 empty] | 9 |  |  | 23 | SET UPS/ TPX - Wovens, Knits, Bottoms (M/F) |  | 27 | WORKING ALIGNMENT MEETINGS - Sweaters and Jackets (W) |  | 35 | RAW MAT FABRIC PASS OFF TO SOURCING (T) | non - china mills/suppliers
| 53 | 2020-02-03 | [16 empty] | 8 | CHASE SAMPLES X |  | 22 |  | latest date for art x for strikeoffs at poho (F) (Jackets) | 26 | WORKING ALIGNMENT MEETINGS - Wovens, Knits, Bottoms(W) SET UPS/TPX - Sweaters and Jacket (M/F) PRINT WRAPAROUND (Th) |  | 34
| 54 | 2020-02-10 | [16 empty] | 7 | chase poho (13 wks to month 2 ndc; 17 wks to month 3) |  | 21 |  |  | 25 | SET UPS/ TPX - Wovens, Knits, Bottoms (M/F) |  | 33 | FABRIC SHOWBACK (T)
| 55 | 2020-02-17 | [16 empty] | 6 |  |  | 20 |  | Sweater and Jacket samples x | 24 |  |  | 32 | INITIAL SEASONAL CONCEPT - WALL BUILD OUT (M)
| 56 | 2020-02-24 | [16 empty] | 5 |  |  | 19 | SAMPLE REVIEW JACKETS (T) | latest date for art x for strikeoffs at poho (F) | 23 |  |  | 31 | WALL COMPLETE - PATTERN, PRINT, COLOR (M) | Review initial fabric with Colby and buying leads
| 57 | 2020-03-02 | [14 empty] | Month 3 ndc |  | 4 | SHIP VSSL |  | 18 | FPR JACKETS (T) POHO JACKETS (Th) | Woven, knits, bottoms samples x | 22 | SAMPLE REVIEW PREP (T) | latest date for art x for hand looms/strikeoffs at poho (F) | 30 | LAUNCH YARDAGE/ART X (F) | ORDER SAMPLE AND MOCKING YDGE
| 58 | 2020-03-09 | [16 empty] | 3 |  |  | 17 | SAMPLE REVIEW PREP (T) EARLY COMMIT/ FABRIC BOOKING MEETING (Th) |  | 21 | SAMPLE REVIEW JACKETS (T) EARLY COMMIT/ FABRIC BOOKING MEETING (Th) |  | 29 |  | MOCKING YARDAGE SENT
| 59 | 2020-03-16 | [16 empty] | 2 | SHIP AIR |  | 16 | SAMPLE REVIEW (T) | Align on chase ideas for Month 2/3 Strikeoffs x | 20 | FPR JACKETS (T) POHO JACKETS (Th) | Woven, knits, bottoms samples x latest date for art x for hand looms/strikeoffs at poho (F) | 28 |  | MOCKING BEGINS
| 60 | 2020-03-23 | [16 empty] | 1 |  |  | 15 | FPR (Th) POHO (F) | 7 working days from Sample review to fpr; poho on Friday | 19 | SAMPLE REVIEW (T) | Align on chase ideas for Month 2/3 Strikeoffs x | 27 |  | MOCKING
| 61 | 2020-03-30 | [16 empty] | 0 | NDC |  | 14 | Chase Meeting (T) |  | 18 | FPR (Th) POHO (F) | 7 working days from Sample review to fpr; poho on Friday | 26 | SEASONAL CONCEPT (T) AND LINE PLAN (Th) PATTERN OVERVIEW (T)
| 62 | 2020-04-06 | [19 empty] | 13 | Chase set ups/tpx |  | 17 |  |  | 25 | WORKING ALIGNMENT MEETINGS - Sweaters and Jackets (W)
| 63 | 2020-04-13 | [19 empty] | 12 |  |  | 16 |  |  | 24 | WORKING ALIGNMENT MEETINGS - Wovens, Knits, Bottoms(W)
| 64 | 2020-04-20 | [19 empty] | 11 |  |  | 15 |  |  | 23 | SET UPS/TPX - Sweaters and Jacket (M/F)
| 65 | 2020-04-27 | [19 empty] | 10 | CHASE SAMPLES X |  | 14 |  |  | 22 | SET UPS/ TPX - Wovens, Knits, Bottoms (M/F) PRINT WRAPAROUND (Th) |  | 36 | RAW MAT FABRIC PASS OFF TO SOURCING (T)
| 66 | 2020-05-04 | [19 empty] | 9 | chase poho (13 wks to month 2 ndc; 17 wks to month 3) |  | 13 |  |  | 21 |  |  | 35
| 67 | 2020-05-11 | [19 empty] | 8 |  |  | 12 |  |  | 20 |  | latest date for art x for strikeoffs at poho (F) | 34 | FABRIC SHOWBACK (T)
| 68 | 2020-05-18 | [19 empty] | 7 |  |  | 11 |  |  | 19 |  | Sweater and Jacket samples x | 33 | INITIAL SEASONAL CONCEPT - WALL BUILD OUT (M)
| 69 | 2020-05-25 | [19 empty] | 6 |  |  | 10 |  |  | 18 | SAMPLE REVIEW SWEATERS AND JACKETS (T) | Woven, knits, bottoms samples x | 32 | WALL COMPLETE - PATTERN, PRINT, COLOR (M) | Review initial fabric with Colby and buying leads
| 70 | 2020-06-01 | [19 empty] | 5 |  |  | 9 |  |  | 17 | SAMPLE REVIEW PREP (T) EARLY COMMIT/ FABRIC BOOKING MEETING (Th) FPR (Tu) POHO SWEATERS AND JACKETS (Th) |  | 31 | LAUNCH YARDAGE/ART X (F) | ORDER SAMPLE AND MOCKING YDGE
| 71 | 2020-06-08 | [19 empty] | 4 | SHIP VSSL |  | 8 |  |  | 16 | SAMPLE REVIEW (T) | Align on chase ideas for Month 2/3 Strikeoffs x | 30 |  | MOCKING YARDAGE SENT
| 72 | 2020-06-15 | [19 empty] | 3 |  |  | 7 |  |  | 15 | FPR (Th) POHO (F) | 7 working days from Sample review to fpr; poho on Friday | 29 |  | MOCKING BEGINS
| 73 | 2020-06-22 | [19 empty] | 2 | SHIP AIR |  | 6 |  |  | 14 | Chase Meeting (T) |  | 28 |  | MOCKING
| 74 | 2020-06-29 | [19 empty] | 1 |  |  | 5 | SHIP VSSL |  | 13 | Chase set ups/tpx - Non China |  | 27 | SEASONAL CONCEPT (T) AND LINE PLAN (Th) PATTERN OVERVIEW (T)
| 75 | 2020-07-06 | [19 empty] | 0 | NDC |  | 4 |  |  | 12 |  |  | 26 | WORKING ALIGNMENT MEETINGS - Sweaters and Jackets (W)
| 76 | 2020-07-13 | [22 empty] | 3 |  |  | 11 |  |  | 25 | WORKING ALIGNMENT MEETINGS - Wovens, Knits, Bottoms(W)
| 77 | 2020-07-20 | [22 empty] | 2 | SHIP AIR |  | 10 | CHASE SAMPLES X |  | 24 | SET UPS/TPX - Sweaters and Jacket (M/F)
| 78 | 2020-07-27 | [22 empty] | 1 |  |  | 9 | chase poho (13 wks to month 2 ndc; 17 wks to month 3) |  | 23 | SET UPS/ TPX - Wovens, Knits, Bottoms (M/F) PRINT WRAPAROUND (Th)
| 79 | 2020-08-03 | [22 empty] | 0 | NDC |  | 8 |  |  | 22
| 80 | 2020-08-10 | [25 empty] | 7 |  |  | 21 |  | latest date for art x for strikeoffs at poho (F)
| 81 | 2020-08-17 | [25 empty] | 6 |  |  | 20 |  | Sweater and Jacket samples x
| 82 | 2020-08-24 | [25 empty] | 5 |  |  | 19 | SAMPLE REVIEW SWEATERS AND JACKETS (T)
| 83 | 2020-08-31 | [25 empty] | 4 | SHIP VSSL |  | 18 | FPR (Tu) POHO SWEATERS AND JACKETS (Th) | Woven, knits, bottoms samples x
| 84 | 2020-09-07 | [25 empty] | 3 |  |  | 17 | SAMPLE REVIEW PREP (T) EARLY COMMIT/ FABRIC BOOKING MEETING (Th)
| 85 | 2020-09-14 | [25 empty] | 2 | SHIP AIR |  | 16 | SAMPLE REVIEW (T) | Align on chase ideas for Month 2/3 Strikeoffs x
| 86 | 2020-09-21 | [25 empty] | 1 |  |  | 15 | FPR (Th) POHO (F) | 7 working days from Sample review to fpr; poho on Friday
| 87 | 2020-09-28 | [25 empty] | 0 | NDC |  | 14 | Chase Meeting (T)
| 88 | 2020-10-05 | [28 empty] | 13 | Chase set ups/tpx - Non China
| 89 | 2020-10-12 | [28 empty] | 12
| 90 | 2020-10-19 | [28 empty] | 11
| 91 | 2020-10-26 | [28 empty] | 10 | CHASE SAMPLES X
| 92 | 2020-11-02 | [28 empty] | 9 | chase poho (13 wks to month 2 ndc; 17 wks to month 3)
| 93 | 2020-11-09 | [28 empty] | 8
| 94 | 2020-11-16 | [28 empty] | 7
| 95 | 2020-11-23 | [28 empty] | 6
| 96 | 2020-11-30 | [28 empty] | 5
| 97 | 2020-12-07 | [28 empty] | 4 | SHIP VSSL
| 98 | 2020-12-14 | [28 empty] | 3
| 99 | 2020-12-21 | [28 empty] | 2 | SHIP AIR
| 100 | 2020-12-28 | [28 empty] | 1
| 101 | 2021-01-04 | [28 empty] | 0 | NDC
Formulas:
Week Start (Monday) = [Week Start (Monday), row above]+7

## Calendar Detailed
Go back to Table of Contents
Cell Formatting Legend
| Yellow | Cells that contain key anchor dates that the calendar is built off of
| Blue | Cells that contain dates that were adjusted due to holidays
| Red | Cells that contain dates that were adjusted due to seasonal overlap
| Orange | BTS 2019 is for formula reference only
| Green | Cells that contain dates during CNY shutdown and need to be reviewed
| Peach | Cells that contain dates during Diwali shutdown and need to be reviewed
| Pink | Cells that contain China 5/1 and 10/1 holiday
2020-01-11
| Phase | Calendar Item | Type | Standard # Days | Working Days | Before/After | Dependency | Day of Week | Early BTS 2020 | Fall 2020 | HOLIDAY 2020 (10/1 & 11/1) | TRANS 2020 (12/1 & 1/1) | SPRING 2021 (2/1,3/1) | SUMMER 2021 (5/1, 6/1,7/1) | FALL 2021 (8/1 & 9/1) | HOLIDAY (10/1,11/1,12/1) | HOLIDAY 2021 (10/1 & 11/1) |  | SUMMER 2021 (4/1,5/1) | BTS 2021 (6/1,7/1) | FALL 2021 (8/1,9/1) | HOL 2021 (10/1,11/1) | TRANS 2021 (12/1,1/1)
|  | Raw Materials Handoff (10 wks before sketch review 1) | Meeting | 14 | #REF! | Before | Fabric Showback (8 wks before sketch review 1) + PRE DEV REQUEST FOR SKETH REVIEW. | Wednesday | #REF! | 2019-10-15 | #REF! | N/A | 2020-06-03 | #REF! | #REF! | #REF! | #REF! |  | 2020-07-29 | 2020-09-30 | 2020-12-02 | 2021-02-03 | 2021-04-07
|  | Fabric Showback (8 wks before sketch review 1) + PRE DEV REQUEST FOR SKETH REVIEW. | Meeting | 6 | #REF! | Before | Initial Seasonal Concept- Begin wall build out (7 weeks before sketch review 1) | THURSDAY | #REF! | 2019-10-29 | #REF! | N/A | 2020-06-18 | #REF! | #REF! | #REF! | #REF! | #REF! | 2020-08-13 | 2020-10-15 | 2020-12-17 | 2021-02-18 | 2021-04-22
|  | Initial Seasonal Concept- Begin wall build out (7 weeks before sketch review 1) | Meeting | 7 | #REF! | Before | Wall complete - Print/pattern/color | THURSDAY | #REF! | 2019-11-04 | #REF! | N/A | 2020-06-25 | #REF! | #REF! | #REF! | #REF! |  | 2020-08-20 | 2020-10-22 | 2020-12-24 | 2021-02-25 | 2021-04-29
|  | Print/Artwork /Wash TP x for Sample Rolls (y/d and pfd roll launch for protos 5 wks(new and existing fabrics) | Deadline | 25 | #REF! | Before | Seasonal Concept Presentation | Friday | #REF! | 2019-11-22 | #REF! | N/A | 2020-07-24 | #REF! | #REF! | #REF! | TUESDAY, DEC 15TH 2020 |  | 2020-09-18 | 2020-11-20 | 2021-01-22 | 2021-03-26 | 2021-05-28
|  | Request mocking yardage sent to Philly | Deadline | 25 | #REF! | Before | Seasonal Concept Presentation | Tuesday | #REF! | 2019-11-22 | #REF! | N/A | 2020-07-07 | #REF! | #REF! | #REF! | #REF! |  | 2020-08-25 | 2020-11-03 | 2021-01-05 | 2021-03-09 | 2021-05-11
|  | Wall complete - Print/pattern/color | Meeting | 11 | #REF! | Before | Print/Artwork /Wash TP x for Sample Rolls (y/d and pfd roll launch for protos 5 wks(new and existing fabrics) | Tuesday | #REF! | 2019-11-11 | #REF! | N/A | 2020-06-30 | #REF! | #REF! | #REF! | #REF! |  | 2020-08-18 | 2020-10-27 | 2020-12-29 | 2021-03-02 | 2021-05-04
|  | Sample yarn order due | Deadline | 33 |  | Before | Sketch review week 1 | Tuesday | #REF! | 2020-12-06 | #REF! | N/A | 2020-07-14 | #REF! | #REF! | #REF! | Tuesday, January 19th |  | 2020-09-01 | 2020-11-10 | 2021-01-12 | 2021-03-16 | 2021-05-18
|  | Seasonal Concept Presentation | Milestone | 2 | #REF! | Before | #REF! | Tuesday | #REF! | 2019-12-17 | #REF! | N/A | 2020-07-28 | #REF! | #REF! | #REF! | #REF! |  | 2020-09-15 | 2020-11-24 | 2021-01-26 | 2021-03-30 | 2021-06-01
|  | Line Plan Review (thursdays) | Meeting | 2 | #REF! | Before | #REF! | THURSDAY | #REF! | 2019-12-17 | #REF! | N/A | 2020-07-30 | #REF! | #REF! | #REF! | #REF! |  | 2020-09-17 | 2020-11-26 | 2021-01-28 | 2021-04-01 | 2021-06-03
|  | Sketch review week 1 | Meeting | 7 |  | Before | Sketch review week 2 | THURSDAY | #REF! | 2020-02-03 | #REF! | N/A | 2020-08-13 | #REF! | #REF! | #REF! | #REF! |  | 2020-10-08 | 2020-12-10 | 2021-02-11 | 2021-04-15 | 2021-06-17
, jackets |  | WEEK 1 cost engineering start | Deadline |  |  |  |  | Monday | #REF! | 2020-02-05 | #REF! | N/A | 2020-08-17 | #REF! | #REF! | #REF! | #REF! |  | 2020-10-12 | 2020-12-14 | 2021-02-15 | 2021-04-19 | 2021-06-21
|  | Sketch review week 2 | Meeting | 5 | #REF! | Before | WEEK 1 - SET UPS | THURSDAY | #REF! | 2020-02-10 | #REF! | N/A | 2020-08-20 | #REF! | 2020-12-08 | #REF! | #REF! |  | 2020-10-15 | 2020-12-17 | 2021-02-18 | 2021-04-22 | 2021-06-24
|  | Deadline (eod) for style packs in order of priority fit | Deadline | 2 | #REF! | After | Sketch review week 2 | Friday |  | 2020-02-12 |  | N/A | 2020-08-22 |  | 2020-12-10 |  |  |  | 2020-10-17 | 2020-12-19 | 2021-02-20 | 2021-04-24 | 2021-06-26
|  | Deadline (eod) for detailed style packs with retails, month, skus, col v/print and unit range | Deadline | 4 | #REF! | After | Deadline (eod) for style packs in order of priority fit | Tuesday | #REF! | 2020-02-16 | #REF! | N/A | 2020-08-23 | #REF! | 2020-12-11 | #REF! | #REF! |  | 2020-10-18 | 2020-12-20 | 2021-02-21 | 2021-04-25 | 2021-06-27
|  | WEEK 2 cost engineering start | Deadline |  |  |  |  | Monday | #REF! | 2020-02-12 | #REF! | N/A | 2020-08-24 | #REF! | 2020-12-10 | #REF! | #REF! |  | 2020-10-19 | 2020-12-21 | 2021-02-22 | 2021-04-26 | 2021-06-28
|  | Print/Artwork Review Wraparound | Meeting | 15 | #REF! | Before | Latest artwork TP x date for strike offs X | Thursday | #REF! | 2020-02-13 | #REF! | N/A | 2020-08-27 | #REF! | #REF! | #REF! | #REF! |  | 2020-10-22 | 2020-12-24 | 2021-02-25 | 2021-04-29 | 2021-07-01
|  | WEEK 1 - SET UPS | Meeting | 4 | #REF! | Before | WEEK 1 - TPX | Monday | #REF! | 2020-02-10 | #REF! | N/A | 2020-08-24 | #REF! | #REF! | #REF! | #REF! |  | 2020-10-19 | 2020-12-21 | 2021-02-22 | 2021-04-26 | 2021-06-28
|  | WEEK 1 - TPX | Deadline | 28 | #REF! | Before | #REF! | Friday | #REF! | 2020-02-14 | #REF! | N/A | 2020-08-28 | #REF! | #REF! | #REF! | #REF! |  | 2020-10-23 | 2020-12-25 | 2021-02-26 | 2021-04-30 | 2021-07-02
|  | WEEK 2 - SET UPS | Meeting | 4 | #REF! | Before | WEEK 2 - TP X | Monday | #REF! | 2020-02-17 | #REF! | N/A | 2020-08-31 | #REF! | #REF! | #REF! | #REF! |  | 2020-10-26 | 2020-12-28 | 2021-03-01 | 2021-05-03 | 2021-07-05
|  | WEEK 2 - TP X | Deadline | 28 | #REF! | Before | Sample x | Friday | #REF! | 2020-02-21 | #REF! | N/A | 2020-09-04 | #REF! | #REF! | #REF! | #REF! |  | 2020-10-30 | 2021-01-01 | 2021-03-05 | 2021-05-07 | 2021-07-09
|  | Latest artwork TP x date for strike offs X | Deadline | 28 | #REF! | Before | Strike offs X | Wednesday | #REF! | 2020-02-28 | #REF! | 2020-07-22 | 2020-09-16 | #REF! | #REF! | #REF! | #REF! |  | 2020-11-11 | 2021-01-13 | 2021-03-17 | 2021-05-19 | 2021-07-21
|  | Sample x | Deadline | 4 | #REF! | Before | Team prep for Sample review | Wednesday | #REF! | 2020-03-13 | #REF! | N/A | 2020-09-30 | #REF! | #REF! | #REF! | #REF! |  | 2020-11-25 | 2021-01-27 | 2021-03-31 | 2021-06-02 | 2021-08-04
|  | CLO set ups pre-finalization (Woven tops & Soft woven bottoms) | Meeting |  |  |  |  | THURSDAY | #REF! | 2020-03-10 | #REF! | N/A | 2020-09-24 | #REF! | #REF! | #REF! | #REF! |  | 2020-11-19 | 2021-01-21 | 2021-03-25 | 2021-05-27 | 2021-07-29
|  | Team prep for Sample review | Meeting | 7 | 4 | Before | Sample Review/Finalization | Monday | #REF! | 2020-03-19 | #REF! | 2020-08-03 | 2020-10-05 | #REF! | #REF! | #REF! | #REF! |  | 2020-11-30 | 2021-02-01 | 2021-04-05 | 2021-06-07 | 2021-08-09
|  | Sample Review/Finalization | Milestone | 9 | #REF! | Before | #REF! | THURSDAY | #REF! | 2020-03-24 | #REF! | 2020-08-06 | 2020-10-08 | #REF! | #REF! | #REF! | #REF! |  | 2020-12-03 | 2021-02-04 | 2021-04-08 | 2021-06-10 | 2021-08-12
|  | Early Fabric commit meeting | Meeting | 2 | #REF! | After | Team prep for Sample review | Friday | #REF! | 2020-03-26 | #REF! | 2020-08-07 | 2020-10-09 | #REF! | #REF! | #REF! | #REF! |  | 2020-12-04 | 2021-02-05 | 2021-04-09 | 2021-06-11 | 2021-08-13
|  | Strike offs X | Deadline | 7 |  | Before | #REF! | Friday | 2020-02-07 | 2020-03-20 | 2020-05-15 | 2020-08-06 | 2020-10-08 | 2020-12-04 | 2021-03-12 | 2021-05-14 | 2021-05-14 |  | 2020-12-03 | 2021-02-04 | 2021-04-08 | 2021-06-10 | 2021-08-12
|  | POHO M1 via AIR + M2 via VSL | Milestone | 116 | #REF! | Before | M1 Ship AIR | THURSDAY | 2020-02-21 | 2020-04-03 | 2020-05-29 | 2020-08-20 | 2020-10-22 | 2020-12-18 | 2021-03-26 | 2021-05-28 | 2021-05-28 |  | 2020-12-17 | 2021-02-18 | 2021-04-22 | 2021-06-24 | 2021-08-26
|  | M1 Ship AIR | Deadline | 12 | #REF! | Before | M1 In DC | Tuesday | 2020-05-20 | 2020-06-29 | 2020-08-25 | 2020-11-17 | 2021-01-19 | 2021-03-23 | 2021-06-22 | 2021-08-24 | 2021-08-24 |  | 2021-03-23 | 2021-05-18 | 2021-07-20 | 2021-09-21 | 2021-11-23
|  | M2 ship VSL | Deadline | 12 | #REF! | Before | M2 In DC | Tuesday |  |  |  | 2020-11-24 | 2021-01-19 | [5 empty] | 2021-03-23 | 2021-05-25 | 2021-07-27 | 2021-09-21 | 2021-11-23
|  | M1 In DC | Deadline | 5th of M1 |  |  | Anchor Date | Tuesday | 2020-07-01 | 2020-08-05 | 2020-10-06 | 2020-12-01 | 2021-02-02 | 2021-05-04 | 2021-08-03 | 2021-10-05 | 2021-10-05 |  | 2021-04-06 | 2021-06-01 | 2021-08-03 | 2021-10-05 | 2021-12-07
|  | M2 In DC | Deadline |  |  |  |  | Tuesday |  |  |  | 2021-01-05 | 2021-03-02 | [5 empty] | 2021-05-04 | 2021-07-06 | 2021-09-07 | 2021-11-02 | 2022-01-04
[9 empty] | CNY SHUTDOWN 1/11-2/11 (1/25) | CNY SHUTDOWN 1/11-2/11 (1/25) |  |  | CNY SHUTDOWN 1/11-2/11 | CNY SHUTDOWN 1/29-3/1 | CNY SHUTDOWN 1/29-3/1 | CNY SHUTDOWN 1/29-3/1 | CNY SHUTDOWN 1/29-3/1 |  | CNY SHUTDOWN 1/11-2/11 | CNY SHUTDOWN 1/11-2/11 | CNY SHUTDOWN 1/11-2/11
#REF!
#REF!
|  | Chase meeting (TUESDAY AFTER POHO) | Meeting | 6 |  | Before | Chase set ups/tpx (MONDAY AFTER CHASE MEETING) | Tuesday | 2019-01-02 | 2019-03-26 | 2019-06-25 | 2019-09-24 | 2020-01-07 | 2020-03-31 | 2020-06-23 | 2020-09-29
|  | Chase set ups/tpx (MONDAY AFTER CHASE MEETING) | Deadline | 25 |  | Before | Chase samples x (2 WEEKS POST TPX ) | Monday | 2019-01-07 | 2019-04-01 | 2019-07-01 | 2019-09-30 | 2020-01-13 | 2020-04-06 | 2020-06-29 | 2020-10-05 | -25 | -25 | -25 | -25 | -25
|  | Chase samples x (2 WEEKS POST TPX ) | Deadline | 7 |  | Before | Chase poho ( 1 WEEK AFTER SAMPLE REVIEW) | Friday | 2019-02-01 | 2019-04-26 | 2019-07-26 | 2019-09-27 | 2020-01-17 | 2020-05-01 | 2020-07-24 | 2020-10-30
|  | Chase poho ( 1 WEEK AFTER SAMPLE REVIEW) | Meeting | 59 |  | Before | Phase 1 In DC | Friday | 2019-02-08 | 2019-05-03 | 2019-08-02 | 2019-11-01 | 2020-02-14 | 2020-05-08 | 2020-07-31 | 2020-11-06
|  | Prelim Top 10 | Deadline | 7 | 5 | Before | Final Top 10 | Tuesday | 2019-01-21 | 2019-04-15 | 2019-07-15 | 2019-10-16 | 2020-01-15 | 2020-04-22 | 2020-07-22 | 2020-10-21 | 2020-02-05 | 2020-04-06 | 2020-06-08 | 2020-08-05 | 2020-10-06
|  | Final Top 10 | Deadline | 70 | 50 | Before | Phase 1 In DC | Tuesday | 2019-01-28 | 2019-04-22 | 2019-07-22 | 2019-10-23 | 2020-01-22 | 2020-04-29 | 2020-07-29 | 2020-10-28 | 2020-02-12 | 2020-04-13 | 2020-06-15 | 2020-08-12 | 2020-10-13
|  | Phase 1 Ship | Deadline | 12 | 8 | Before | Phase 1 In DC | Wednesday | 2019-03-27 | 2019-06-19 | 2019-09-18 | 2019-12-20 | 2020-03-20 | 2020-06-26 | 2020-09-25 | 2020-12-25 | 2020-04-10 | 2020-06-10 | 2020-08-12 | 2020-10-09 | 2020-12-10
|  | Phase 1 In DC | Deadline | 5th of M1 |  |  | Anchor Date | Monday | 2019-04-08 | 2019-07-01 | 2019-09-30 | 2020-01-01 | 2020-04-01 | 2020-07-08 | 2020-10-07 | 2021-01-06 | 2020-04-22 | 2020-06-22 | 2020-08-24 | 2020-10-21 | 2020-12-22
[12 empty] | 89 | 89 | 95 | 88 | 88 | 88 | 0 | 96 | 89 | 89 | 89 | 89
[12 empty] | 14 | 14 | 42 | 42 | 42 | 42 | 0 | 14 | 14 | 14 | 14 | 14
[12 empty] | 42 | 42 | 0 | 0 | 0 | 0 | 0 | 42 | 42 | 42 | 42 | 42
[9 empty] | 2020-02-14: 222; 2020-05-08: #REF!; 2020-07-31: #REF!; 2020-11-06: #REF! | #REF! | 0 | 229 | 222 | 222 | 222 | 222
[12 empty] | 103 | 103 | 137 | 130 | 130 | 130 | 0 | 110 | 103 | 103 | 103 | 103
Wk1 + Wk2 set ups will be actioned together
Formulas:
Working Days = NETWORKDAYS(INDEX(#REF!,MATCH([Calendar Item],C12:C42,0)),INDEX(#REF!,MATCH([Dependency],C12:C42,0)))-1
Working Days = NETWORKDAYS(INDEX(V13:V54,MATCH([Calendar Item],C13:C54,0)),INDEX(V13:V54,MATCH([Dependency],C13:C54,0)))-1
Fall 2020 = IFERROR(IF([Before/After]="Before",INDEX(K:K,MATCH([Dependency],$C:$C,0))-[Standard # Days],INDEX(K:K,MATCH([Dependency],$C:$C,0))+[Standard # Days]),"")
SPRING 2021 (2/1,3/1) = [SPRING 2021 (2/1,3/1), row above]+2
SPRING 2021 (2/1,3/1) = [SPRING 2021 (2/1,3/1), row below]-89
SUMMER 2021 (4/1,5/1) = [SUMMER 2021 (4/1,5/1), row below]-14
SUMMER 2021 (4/1,5/1) = [SUMMER 2021 (4/1,5/1), row above]+2
BTS 2021 (6/1,7/1) = [BTS 2021 (6/1,7/1), row above]+2
BTS 2021 (6/1,7/1) = [BTS 2021 (6/1,7/1), row below]-3
FALL 2021 (8/1,9/1) = [FALL 2021 (8/1,9/1), row above]+2
FALL 2021 (8/1,9/1) = [FALL 2021 (8/1,9/1), row below]-3
HOL 2021 (10/1,11/1) = [HOL 2021 (10/1,11/1), row above]+2
HOL 2021 (10/1,11/1) = [HOL 2021 (10/1,11/1), row below]-3
TRANS 2021 (12/1,1/1) = [TRANS 2021 (12/1,1/1), row above]+4
TRANS 2021 (12/1,1/1) = [TRANS 2021 (12/1,1/1), row below]-3
TRANS 2020 (12/1 & 1/1) = [TRANS 2020 (12/1 & 1/1), row below]-3
TRANS 2020 (12/1 & 1/1) = [TRANS 2020 (12/1 & 1/1), row above]+1
Early BTS 2020 = [Early BTS 2020, row below]-14
HOLIDAY 2020 (10/1 & 11/1) = [HOLIDAY 2020 (10/1 & 11/1), row below]-88
SUMMER 2021 (5/1, 6/1,7/1) = [SUMMER 2021 (5/1, 6/1,7/1), row below]-95
FALL 2021 (8/1 & 9/1) = [FALL 2021 (8/1 & 9/1), row below]-88
HOLIDAY (10/1,11/1,12/1) = [HOLIDAY (10/1,11/1,12/1), row below]-88
HOLIDAY 2021 (10/1 & 11/1) = [HOLIDAY 2021 (10/1 & 11/1), row below]-88
HOLIDAY 2021 (10/1 & 11/1) = IFERROR(IF([Before/After]="Before",INDEX(R:R,MATCH([Dependency],$C:$C,0))-[Standard # Days],INDEX(R:R,MATCH([Dependency],$C:$C,0))+[Standard # Days]),"")
Note on P33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SAMPLES NEED TO X PRE CNY
Note on O37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CNY EARLY COMMIT STLES DUE AS WELL

## Sheet2
2021-01-19 | 2020-11-18 |  | 2020-11-20
2020-10-22 | 89 | 8/6 sample review | 2020-08-20
89 | 2020-08-21 | 8/20 POHO | 92

## Sheet1 (hidden)
11/25 – Order cones to have in house 2 weeks prior to sketch review to knit with (COMPLETED)
10/17 – Knitdown requests for sketch review
1/3 – Yarn Order for Sample Poundage due (COMPLETED)
2/24 – Buying sketch review
2/25 – PD Exceptions
3/9 - SET UP
3/13 – TP X + Lab Dip Requests due for POHO
4/6 – Sample x
4/17 – POHO | 2020-04-17
8/5 – NDC M1 | 2020-08-05 | 110

## Holidays
Go back to Table of Contents
Note: Please adjust CNY shutdown start and end date for each year
Holiday | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
New Year's Day | 2017-01-02 | 2018-01-01 | 2019-01-01 | 2020-01-01 | 2021-01-01 | 2021-12-31 | 2023-01-02 | 2024-01-01 | 2025-01-01
Memorial Day | 2017-05-26 | 2018-05-25 | 2019-05-24 | 2020-05-22 | 2021-05-28 | 2022-05-27 | 2023-05-26 | 2024-05-24 | 2025-05-23
Memorial Day | 2017-05-29 | 2018-05-28 | 2019-05-27 | 2020-05-25 | 2021-05-31 | 2022-05-30 | 2023-05-29 | 2024-05-27 | 2025-05-26
Independence Day | 2017-07-04 | 2018-07-04 | 2019-07-04 | 2020-07-03 | 2021-07-05 | 2022-07-04 | 2023-07-04 | 2024-07-04 | 2025-07-04
Labor Day | 2017-09-01 | 2018-08-31 | 2019-08-30 | 2020-09-04 | 2021-09-03 | 2022-09-02 | 2023-09-01 | 2024-08-30 | 2025-08-29
Labor Day | 2017-09-04 | 2018-09-03 | 2019-09-02 | 2020-09-07 | 2021-09-06 | 2022-09-05 | 2023-09-04 | 2024-09-02 | 2025-09-01
Thanksgiving Day | 2017-11-23 | 2018-11-22 | 2019-11-28 | 2020-11-26 | 2021-11-25 | 2022-11-24 | 2023-11-23 | 2024-11-28 | 2025-11-27
Christmas Day | 2017-12-25 | 2018-12-25 | 2019-12-25 | 2020-12-25 | 2021-12-24 | 2022-12-26 | 2023-12-25 | 2024-12-25 | 2025-12-25
CNY Shutdown Start Date | 2017-01-21 | 2018-02-02 | 2019-01-22 | 2020-01-11 | 2021-01-29 | 2022-01-18 | 2023-01-08 | 2024-01-27 | 2025-01-15
CNY | 2017-01-28 | 2018-02-16 | 2019-02-05 | 2020-01-25 | 2021-02-12 | 2022-02-01 | 2023-01-22 | 2024-02-10 | 2025-01-29
CNY Shutdown End Date | 2017-02-04 | 2018-03-05 | 2019-02-22 | 2020-02-11 | 2021-03-01 | 2022-02-18 | 2023-02-08 | 2024-02-27 | 2025-02-15
Diwali Shutdown Start Date |  | 2018-11-05 | 2019-10-24 | 2020-11-14 | 2021-11-03 | 2022-10-24 | 2023-10-11 | 2024-10-31 | 2025-10-24
Diwali |  | 2018-11-07 | 2019-10-27 | 2020-11-14 | 2021-11-04 | 2022-10-24 | 2023-10-12 | 2024-11-01 | 2025-10-25
Diwali Shutdown End Date |  | 2018-11-09 | 2019-11-01 | 2020-11-20 | 2021-11-11 | 2022-10-28 | 2023-10-19 | 2024-11-08 | 2025-10-31
China Golden Week | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01
China Golden Week | 2017-05-01 | 2018-05-01 | 2019-05-01 | 2020-05-01 | 2021-05-01 | 2022-05-01 | 2023-05-01 | 2024-05-01 | 2025-05-01